SocialVideoDownloader 6-Week Roadmap

Repo-based plan generated from the codebase on March 14, 2026

Planning window: March 16, 2026 to April 26, 2026

# Current Baseline

The repo is at a working foundation stage: the multi-module structure, Hilt wiring, Room skeleton, Compose navigation, and dynamic Material 3 theme are implemented.

Current user-facing functionality is still placeholder-only: Download and History screens do not yet offer URL intake, metadata preview, download execution, or history management.

The application already initializes YoutubeDL, FFmpeg, and Aria2c at startup, which lowers platform risk for week 2 and week 3 feature work.

The current architecture constrains future work: Compose only, no XML layouts, no fragments, no kapt, KSP-based DI, Room-backed persistence, and :core:domain must remain a pure Kotlin module.

Engineering gaps visible in the repo: no ViewModels or use-case layer yet, no test sources yet, and ktlint currently fails because Qualifiers.kt should be renamed to match IoDispatcher.

# Milestones

Milestone 1 - End of Week 2: The placeholder Download screen becomes a functional intake flow that can validate a URL, extract metadata, and show a preview with clear errors.

Milestone 2 - End of Week 4: The app completes an end-to-end MVP: start a download, persist state in Room, and manage records from a real History screen.

Milestone 3 - End of Week 6: The app reaches beta readiness with resilience work, critical test coverage, API-level validation, and a release checklist.

# Week-by-Week Plan

| Week | Focus | Weekly Goals | Deliverables / Exit Criteria |
| --- | --- | --- | --- |
| Week 1 Mar 16-22 | Foundation hardening and delivery architecture | Rename IoDispatcher file for clean lint, define ViewModel/use-case/state pattern, wire feature modules to repository contracts, decide storage strategy, and add first smoke tests. | assembleDebug and ktlintCheck are green; feature architecture notes exist; first ViewModels and use-case skeletons land. |
| Week 2 Mar 23-29 | URL intake and metadata extraction MVP | Build the download input UI, validate supported URLs, add a core:data wrapper around metadata extraction, surface title/thumbnail/format info, and persist draft download records. | A user can paste a URL and see metadata or a clear error from the Download screen. |
| Week 3 Mar 30-Apr 5 | Download execution and progress tracking | Implement start/cancel actions, choose the initial format policy, stream progress into UI state, write files to the selected destination, and persist live status updates in Room. | A supported URL can be downloaded end to end with visible progress and a stored record. |
| Week 4 Apr 6-12 | History screen and file actions | Replace the placeholder History UI with a repository-backed list, show thumbnails/status/timestamps, add open-share-delete actions, support retry for failed items, and finalize any schema changes. | History becomes a usable management surface instead of a placeholder text screen. |
| Week 5 Apr 13-19 | Resilience and background behavior | Add the long-running work model needed for downloads that outlive the screen, handle low storage and interruption cases, prevent duplicate jobs, and expand unit/instrumented coverage for critical flows. | Downloads behave predictably across app backgrounding, failures, and retries. |
| Week 6 Apr 20-26 | Beta hardening and release prep | Run QA across API 26, 31, and 36 targets, fix accessibility and copy gaps, review backup rules and file cleanup behavior, tighten performance, and produce release notes plus a known-issues list. | A beta candidate build, a concise test checklist, and a prioritized post-beta backlog are ready. |

# Dependencies

A week 1 product decision is required on storage: app-private files are faster to ship, while MediaStore or Downloads integration is better for user visibility but adds API 26-36 complexity.

A week 1 decision is also needed on the first supported download behavior: default best MP4 only versus a visible format picker. That choice affects week 2 metadata UX and week 3 execution scope.

The roadmap assumes the existing six-module dependency direction stays intact: feature modules depend on core modules, and :core:domain remains Android-free.

Week 5 resilience work likely requires adding a background execution mechanism such as WorkManager or a foreground-service approach, which is not present in the current repo.

The delivery pace assumes the current toolchain remains stable: Android SDK 36, JDK 17, Compose BOM 2026.03.00, Hilt, Room, and the youtubedl-android stack already declared in the repo.

# Risks

Extractor instability is the highest product risk. Social platforms change often, so metadata extraction and download flows can break even when the app code has not changed.

Storage and file-sharing behavior across API 26-36 can easily expand scope. If the app must save directly into public Downloads, expect extra integration and testing time.

Architecture drift is a near-term engineering risk because the repo has no ViewModels, use cases, or screen state model yet. Without a week 1 pattern, feature logic can leak into composables.

Regression risk is already visible because there are no current tests and the repo fails ktlint on a filename rule. Quality gates need to be tightened before download logic grows.

Background and long-running download behavior is not yet designed. If true pause, resume, and process-death recovery are required for MVP, week 5 may spill into week 6.

# Recommended Outcome By End Of Week 6

The app supports one stable end-to-end download path for the highest-priority source URLs.

Users can see progress, review history, retry failures, and open or share completed files.

The codebase keeps the existing modular boundaries intact and gains the minimum ViewModel, use-case, and test structure needed for future feature growth.